## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
0 | FS 1 / Req_1 and 2 | User Registration and Login | In this user has two options.If the user is new then he/she will register otherwise,login with its credentials. | Task #1 | Create the user registeration form jsp so,that new user can enter details. User redirection to fill some of the basic attributes/fields as mentioned below in: (First Name, Last Name, Age, Gender, Contact Number, Email, Password, Weight, State, Area, Pin code, Blood Group) | Critical | Rajat Bishnoi | 18.03.2019 | 22.03.2019 | 6 | M | Completed | The objective of this requirement is to allow the user to Register as a new user and redirect to new user registration form. | User being able to access the homepage & get redirected to the ‘User Registration’ page upon click of ‘Register’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task #2 | Create User Entity ,UserDao,UserController,UserService Layer in Spring MVC to Save and Validate the Data. | Critical | Asheesh Sahu | 18.03.2019 | 22.03.2019 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #3 | Login Validation using database , spring security and redirect to Home Page | Critical | Bhushan Mittal | 18.03.2019 | 22.03.2019 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #4 | Integration All | Medium | Kunal Puri | 18.03.2019 | 22.03.2019 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
1 | FS 2 / Req_3 and 4 | Blood Availability and posting | As a user I want to check the availablity of blood of a particular type and post my blood requirements | Task#1 | Home Page Create to show the requirements details and show the need button(to search the blood availablity) | High | Asheesh Sahu | 25.03.2019 | 28.03.2019 | 6 | M | Completed | The objective of this requirement is to allow the user to donate the blood by the filling the details like(bloodgroup,state,area,pincode) and after that user provide slot booking details. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | If user clicks the need button then it redirect to form to search the blood availablity based on state,area,pincode,bloodgroup | Critical | Kunal Puri | 25.03.2019 | 28.03.2019 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | when user clicks on the search button then database should check the user blood requriments and then if found then show the search results . | Critical | Bhushan Mittal | 25.03.2019 | 28.03.2019 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#4 | if not found then user will be asked to confirm whether she/he wants to post requirements details | High | Asheesh Sahu | 25.03.2019 | 28.03.2019 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#5 | if user choose yes then it redirect to requirement form and ask for details like state,area,pincode and bloodgroup | Critical | Asheesh Sahu | 25.03.2023 | 28.03.2019 | 6 | S | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#6 | if user clicks to save button then validate the data and details. | Critical | Bhushan Mittal | 25.03.2019 | 28.03.2019 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
2 | FS3/ Req_5 | Donation availability | In Homepage Donate button is avaA user willing to donate blood can look for the Blood requirement posting and show interest | Task#1 | If user click the donate then it open the donationform that has attributes (bloodgrup,state,area,pincode,contactno) | Critical | Kunal Puri | 1.03.2019 | 3.04.2019 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | User fill the form that contains some attributes as mentioned below:- Hopsital name,city,bloodgroup,Timeslot | Critical | Rajat Bishnoi | 1.03.2019 | 3.04.2019 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | upon saving the information in the database display the message(user blood requiremts are posted succesfully on the home page) | Medium | Rajat Bishnoi | 1.03.2019 | 3.04.2019 | 6 | S | Completed |  |  | Scrum Master | Average | High | New Requirement
3 | FS4/Req6.1 - 6.4 | User Feedback and posting and show feedback on homepage | User has option to provide the feedback about the hospital | Task#1 | In this user is allow to provide the feedback about the hospital that has attributes like(hospitalname,cityname,feedback) | Low | Bhushan Mittal | 4.04.2019 | 5.04.2019 | 6 | S | Completed | The objective of this requirement is to allow the user to give feedback about the hospital |  | Scrum Master | Average | High | New Requirement
Completed | Kunal Puri | High
In Progress | Bhushan Mittal | Low
Not Started | Rajat Bishnoi | Medium
| Asheesh Sahu | Critical
Future